## Slide 1
1 Skills Cap project complete
£52.7m match funding in quarter
Final round of Skills Capital live
2 projects commenced drawing
1 project breaking ground
211 jobs created.
Milestones in quarter
Local Growth Fund – Oct - Dec 2019 (Q3)
Skills and Economic development project update
Portfolio of projects *total project values and status* |  |  |  |  |  |  |  |  |  | 
Complete |  |  | In Delivery |  |  | In delivery |  |  | Contracts drafting | 
Skills Cap Salford College | 4m |  | Life Sciences | 31m |  | Protos | 17m |  | Cyber Security | 10m
Skills Cap Tameside College/ MBC | 18m |  | GC Productivity programme | 35m |  | Broughton House | 14m |  |  | 
Skills Cap Tside College equipment | 1m |  | Skills Cap Stockport College | 23m |  | Project Q | 24m |  |  | 
Skills Cap GC Salford | 90k |  | MMU - SODA (ISSM) | 35m |  | UOM - Pankhurst | 15m |  |  | 
Skills Cap Mantra | 1m |  | Skills Cap Leigh | 800k |  | Skills Cap Bury College | 7m |  |  | 
UOM - GEIC | 10m |  | Skills Cap Bolton College | 30m |  | Skills Cap Oldham College | 9m |  |  | 
Growth Hub | 512k pa |  | Skills Cap Wigan | 1.8m |  |  |  |  |  | 
Business Support Digital | 1m |  | Skills Cap LTE | 139m |  |  |  |  |  | 
 |  |  | Skills Cap Tside BR | 10m |  |  |  |  |  | 
Total | 36.4m |  |  |  |  | Total | 86m |  | Total | 5m
Financial performance
Comms
£18.9m spent in quarter on Skills and ED&R of a total £28.9m reported in quarter.
Groundbreaking ceremony at MMU School of Digital Arts
Further improvements to LEP website including Skills Capital case study
R3 of Skills Capital went live in this quarter, good response.
Risk Management
Green – 7 AG - 8
Amber – 6
AR – 3 Red - 0
Expected Outputs
£140m LGF allocated for Skills and Economic Development
Attract £210m of match funding
Create 2000 jobs
Create pathways to higher skills
Create centres of excellence for growth sectors
Supporting enterprises
No Change– 19
Risk reduced – 2
Risk increased– 3
24 Projects on Q2 return
Support 5400 additional learners
Notes: GM is on the precipice of being a STEM city – we have everything we need (probably)
The complex ecosystem largely needs bringing together to have a shared understanding of what is there, then collaborate and mobilise together towards the similar objectives. Those who don’t will be left behind.